## Slide 2
Intelma Project Control Tool - IPCT

## Slide 3: Summary – one pager – W15
Planned delivery at risk
Green
Yellow
Red
On track; will complete as planned
Originally planned or completed activity
Key Milestone Legend:
Analisis
Requisites Definition Ready
Pre Study, Logic and Application Definition Ready
1. What has the team done since last met? (Achievements)
Prepared the detailed Requisites Description
Definition of macro view of requisites
2. What will the team do before we meet again? (Next steps)
Continue with Pre Study, prepare the flow for Logic
Scope Details / Initiative phases:
Tool was requested by Intelma Management team
Project was started officially on March 21 We have set a sequence of recurrent meetings every Monday from 10am till 12pm. This file will be send out after all follow up meeting.
This phase aims to be finished on May 25, however we plan to keep doing maintenance, creating other reports, etc. according to Intelma´s demand.
Summary
Initiative Description:
We need to improve the way we are controlling projects nowadays, putting focus not only in Daily Reports but also in controlling of Costs, Hours spent, Type of hours, Allocation, etc.
We also need to have a data base unified for all Daily Reports, what needs to be easy to access and centralized.
Reduce the amount of emails going&back related to project status.
Besides these needs we need to produce some easy reports, what can be used for management purpose, project controlling, quotation, so on.
Pcode format: to be defined.
Developers: Martin Villicaña / Architect: Pablo Gonzalez
Actual/Estimated
Key Milestones
4
“May
11”
Planned
2
March
21
1
W13 2018
W15 2018
W18 2018
W19 2018
W20 2018
W21 2018
W11 2018
W12 2018
4. Codification Ready
5. Development Tests Ready
6. Alpha version launch
7. Debug and Improvements + REV A launch
W12 2018
5
6
May
25
3. Is anything slowing the team down? (Risks and Issues)
N/A
4. What support is required from the Leaders? (attention and action)
Assure 100% assignation for Pablo Gonzalez and Martin for this project
Create an internal project in current tool IPCT for Pablo Gonzalez and Martin time reporting
Provide any support needed to Pablo Gonzalez and Martin in order to assure the milestones as planned
Needed to defined the Server where this application can be stored.
Gray
7
“May
18”
March
21
March
23
3
Will miss planned delivery
4
May
11”
2
March
21
1
5
6
May
25
7
May
18”
March
21
March
23
3
“May
04”
“May
04”

## Slide 4
Thank you
Canadá
866 Place Simon, Saint Laurent
Canada H4M 2W2
+1514 564 3243
Ciudad de México
Av. Ejercito Nacional No. 505 – 1003
Col. Ampliación Granada, Ciudad de México
+52 55 65 88 99 23
www.intelmas.com