## Slide 2
OPM – Ericsson

## Slide 3: Summary – one page – W19
Planned delivery at risk
Green
Yellow
Red
On track; will complete as planned
Originally planned or completed activity
Key Milestone Legend:
Codification
Development Tests Ready
Documentation
1. What has the team done since last met?
Test: Real We are in OPM Test Environtment, and then we’re going to pass to Test Execution phase.
Designing and Development Excection Scripts. Was Developed and pass to test phase.
Fixing the issues in SoftAlarms and Notifications in code, later pass to test again.
2. What will the team do before we meet again? (Next steps)
Finished the OPM Test Environtment and Testing in Test Execution phase.
Developing Installation Script.
Fixed issues in SoftAlarms and Notifications in code.
Scope Details / Initiative phases:
Tool was requested by Telcel.
Project will start officially until have all raw data.
We have set a sequence of recurrent meetings every Monday from 10am till 12pm. This file will be send out after all follow up meeting.
This phase aims to be finished on May 21, however we plan to keep doing maintenance, creating other reports, etc. according to client´s demand.
Summary
Initiative Description:
We need a tool for showing Node problems in less time than the other software tools
FeedBack to the clients for greater capacity to take decisions.
Gui friendly with important data.
Actual/Estimated
Key Milestones
4
May
23
Planned
2
May
21
May
11
1
W20 2018
W21 2018
W22 2018
W23 2018
W24 2018
W25 2018
W26 2018
W272018
4. Installation Package/Test
5. Alpha version Launch
W19 2018
5
3. Is anything slowing the team down? (Risks and Issues)
N/A
4. What support is required from the Leaders? (attention and action)
More Tests and human resources for rich the OPM goals.
Gray
May
17
May
17
3
Will miss planned delivery
4
2
May
11
1
5
3
May
17
May
17
May
21
May
23

## Slide 4: What is OPM?
It is a centralized and unified tool, Web Based, which aims to:
Improve the way Telcel monitor the performance of telecommunications network.
Prevent issues with nodes by alarms.
Have a database unified for generating reports in GUI, what needs to be friendly with the final user.
Provides module to monitor KPI values but node/cell combination, region and network.
Provides the function to create new KPI.
Provides modules to automate monitoring and send notifications and softalarms to the user.
Be friendly, security and assertive.

## Slide 5: benefits
With OPM implemented Telcel user is able to:
Makes Telcel operators troubleshooting faster.
Contribute to decisions making to keep a good performance in the entire network.
Have fast reports about KPI values in network elements.
Create custom type of monitoring reports and KPIs formulas.
Have a centralized data base, friendly and 100% accessible
Less number of issues.

## Slide 6: status of work
Tool was requested by Telcel team
Project will started officially on April 30th
We have set a sequence of recurrent meetings every Monday from 10am till 12pm. This file will be send out after all follow up meeting.
This phase aims to be finished on July 10th, however we plan to keep doing maintenance, creating other reports, etc. according to Intelma´s demand.

## Slide 7: Requisites
Scope The OPM will be an application that will work in a WEB environment that will allow users to enter the activities of monitoring network, manage and generate reports, the general functions of the application are:
Dashboard
KPI Lab
Reports
Notifications
Softalarms
OPM intend to be friendly user and allow to add expansible modules, new reports, etc…

## Slide 8: Requisites
Modules
Accounts In this module the final user has the possibility to manage user profile settings.
Dashboards In this module the final user has the possibility to interact with different widgets (12/24 chart, KPI level, Number of nodes, Worst/Best nodes and last rop KPI), these widgets show KPI information. Also the has the possibility to export dashboards in PDF.
KPI Lab In this module the final user has the possibility to create custom KPI formulas.
Reports In this module the final user has the possibility to create reports from historical data and export them to CSV format.
Loading monitor In this module the final user has the possibility to see the data loading status for each KPI.

## Slide 9: Requisites
Modules
Notifications In this module the final user has the possibility to make automatic monitoring the status of nodes/cells via notifications sent by email/sms or directly to any host.
Softalarms In this module the final user has the possibility to create reports from OSS data and sent them as text file to any host.

## Slide 10: Requisites
User types
The OPM will have 3 user types
Administrator
Operator
User

## Slide 11: Requisites
Regulatory policies
The application will be developed by open license software for this reason Intelma Consulting will not have to pay for the use of any freeware, therefore, the use of these programs will be done through the policies established by this type of licensing.

## Slide 12: Requisites
Hardware Requirements:
Minimum requirements
16 processors (cores and 32 threads) 2.5 GHz 170 GB in RAM (DDR3) 2 TBs on hard disk (for operating system and storage of the BD)
Recommended requirements
16 processors (cores and 32 threads) 2.5 GHz 256 GB in RAM (DDR3) 5 TBs hard drive (for operating system and storage of the BD)

## Slide 13: Requisites
Software Requirements:
BE
Operating System (CentOS 7) Cassandra 3.11 Elasticsearch 6.1.2 RabbitMQ 3.6
  Java 1.8u131 64bits
  FE
  Angular 4, nodejs 7.10
  chartjs,
  angular-moment
  file-saver
  Json2cvs
  Angular Matirial
  nginx 1.13.5-1 (Server)

## Slide 14: Requisites
Other Requirements BE:
Fixed IP public (preferably) Internet access to install dependencies Root permissions for port, firewall and service configurations

## Slide 15: Requisites
Other Requirements FE:
Browser Supported versions
Chrome, Firefox latest
Edge 2 most recent major versions
IE 11

## Slide 16: Team composition & Business case
This is the basic composition of team:
- Software Architect - Pablo Gonzalez pablo.ramirez@intelmas.com
- BE developer - Brayant Monroy brayant.mejia@intelmas.com
- Administrator/BE developer – Cesar Corona cesar.corona@intelmas.com
- FE developer – Martin Rodriguez martin.rodriguez@intelmas.com
- Tester – Alfreddy Hutabarat alfreddy.baringin@intelmas.com

## Slide 17: Team composition & Business case
The estimate cost in hours are:
- SA – 60 days at 100%  480hrs
- BE – 60 days at 100%  480hrs
- Admin/BE – 60 days at 100%  480hrs
- FE – 60 days at 50%  240hrs
- Tester – 20 days 50%  80hrs

## Slide 18: Follow up and feedback
Weekly Progress Report
- Status of Activities
- Update slide 3
Weekly Meeting with:
- Team members

## Slide 19: Needs
Get correct raw data for 3G/4G technologies.

## Slide 20: consideration
Time plan depends of project needs and other unexpected situations.

## Slide 21
Thank you
Canadá
866 Place Simon, Saint Laurent
Canada H4M 2W2
+1514 564 3243
Ciudad de México
Av. Ejercito Nacional No. 505 – 1003
Col. Ampliación Granada, Ciudad de México
+52 55 65 88 99 23
www.intelmas.com