## Slide 2
OPM – Huawei Plugin

## Slide 3: Summary – one page – W15
Planned delivery at risk
Green
Yellow
Red
On track; will complete as planned
Originally planned or completed activity
Key Milestone Legend:
Analysis requirements for Huawei technology
Technical Analysis
Solution proposal and time plan.
1. What has the team done since last met? (Achievements)
N/A
2. What will the team do before we meet again? (Next steps)
Check minimum information (raw data) required to get all OPM modules working for Huawei.
Analysis to implement logic for new raw data for Huawei.
Scope Details / Initiative phases:
Tool was requested by Telcel.
Project will start officially until have all raw data.
We have set a sequence of recurrent meetings every Fryday from 10am till 12pm. This file will be send out after all follow up meeting.
This phase aims to be finished on Jul 20, however we plan to keep doing maintenance, creating other reports, etc. according to client´s demand.
Summary
Initiative Description:
We need a tool for monitoring performance of Huawei nodes in Telcel Network.
We also need to have a database unified for all vendors, what needs to be easy to access and centralized.
We also need to have OPM modules and reports working for Huawei files.
The metrics has to be showed in less than 10 minutes in GUI with all vendors.
Developers: Brayant Monroy, Cesar Corona, Pablo Gonzalez
Architect: Pablo Gonzalez
Actual/Estimated
Key Milestones
4
Jul
06
Planned
2
Jun
22
Apr
30
1
W19 2018
W22 2018
W24 2018
W25 2018
W27 2018
W28 2018
W29 2018
W30 2018
4. Codification Ready
5. Development Tests Ready
6. Alpha version test at local server and ECOSS#4
7. Debug and Improvements + REV A launch
W18 2018
5
6
Jul
20
3. Is anything slowing the team down? (Risks and Issues)
Client has to provide counters catalogue.
4. What support is required from the Leaders? (attention and action)
Get counters catalogue in time.
Get support from external consultor to explain Huawei structure files.
Validation of parsing process results by external consultor expert in Huawei technology.
To get raw data files for entire Huawei network for at least 1 hour.
Gray
7
Jul
13
May
02
May
08
3
Will miss planned delivery
2
Apr
30
1
7
May
02
3
May
08
4
Jun
22
5
Jul
06
6
Jul
13
Jul
20

## Slide 4
Thank you
Canadá
866 Place Simon, Saint Laurent
Canada H4M 2W2
+1514 564 3243
Ciudad de México
Av. Ejercito Nacional No. 505 – 1003
Col. Ampliación Granada, Ciudad de México
+52 55 65 88 99 23
www.intelmas.com