## Slide 2
OPM Modules
Assigned Persons
Pending Tasks.
Agenda:

## Slide 3: OPM Dependencies
Java/Maven – Making/Running Environment for BE applications.
Cassandra – NoSQL Database for big ammount of data.
Elasticsearch – Text search engine for JSON documents.
RabbitMQ – Message Broker Middleware between parser and XML files.
nginx – High Availability Webserver.
HAProxy – Load Balance Software to allow HA in FE and BE.
Zookeeper – Distributed processes and coordination Software.
NodeJS – Multiplatform Environment for running OPM-CLI.
Frontend Installation – Web Interface to generate reports (Connected to all BEs).

## Slide 4: OPM Modules
Retriever - XML Transfer Module from one server to another via FTP/SFTP. It creates symbolic links from these files.
Dispatcher – Compress in bytes XML files from previous modules and puts them into a message broker.
Parser – It process all files from message queue in previous module and stores the data in Database and also transfer them to ES6 where KPI values are calculated and stored.
Backend KPIs – It make queries to ES6 over the KPI calculated data.
Backend Topology – It parses topology files from OSS to store node/region list in DB.
Backend MOs – It makes queries to DB about Nodes/MO data.
Backend Softalarms – It generates softalarms (from KPI BE data) and notifications (OSS/email/SMS).
Users Management BE – Allows OPM user’s management.
Frontend – Web interface to generate reports (Connected to all Backends).
OPM-CLI – Command Line Interface to generate similar reports as FE (Connected to all Backends).

## Slide 5: Responsibles
Installation/Configuration of dependencies/Test in VMWare --> César
Retriever/Dispatcher/Parser/Backend KPI
Backend Topology/Backend MOs/
Backend Softalamars/Users Management Backend --------> Brayant
Frontend/OPM-CLI ---------------------------------------------------------------> Martín
Test in ECOSS#4 ---------------------------------------------------------------> Alfreddy

## Slide 6: Finished Actions (W12)
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS
1 | KPI BE (Load incomplete) - Find root cause | 12/03/18 | César | 20/03/18 | Finished | 20/03/18 | The root cause was at dispatcher’s configuration and was changed.
2 | Retriever FTP - Not working | 12/03/18 | Hendra | 20/03/18 | Finished | 19/03/18 | Solved by remote team (Flags in the code were wrong).
3 | Retriever SFTP - Change configuration variable | 12/03/18 | Hendra | 20/03/18 | Finished | 19/03/18 | Configuration was returned to previous version.
4 | OPM-CLI - Add reports by resolution | 12/03/18 | Martín | 20/03/18 | Finished | 20/03/18 | Now is complete.
5 | OPM Documentation | 05/03/18 | Hendra/Brayant | 15/03/18 | Finished | 15/03/18 | Documentation was delivered but after checked it was not well detailed.
6 | Hardware Dimensioning in VMWare | 21/03/18 | César/Brayant | 22/03/18 | Finished | 23/03/18 | CPU: 24 x 2.65GHz RAM: 192GB. HDD: 4TB.

## Slide 7: Actions W13
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS
1 | Obtain knowledge from remote team over internal logic of OPM modules. | 05/03/18 | César/Brayant | 28/03/18 | Finished | 30/03/18 | Last questions about ES6 behavior was not answered, however, they are not critical. Other issues was clarified.
2 | Test OPM Performance | 12/03/18 | César/Brayant | 13/04/18 | Finished | 11/04/18 | Check Stability: The tool was stable during this week‘s test. Only is missing the test for softalarms that will be performed next week.
3 | Detailed documentation | 15/03/18 | Hendra | 02/04/18 | Finished | 31/03/18 | Only documentation for OPM Retriever (At 26/03/18) and OPM Dispatcher (At 31/03/18 ) was delivered.

## Slide 8: Actions W14
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS
1 | Check status of OPM after running continuously after long weekend. | 02/04/18 | César | 02/04/18 | Finished | 02/04/18 | There was issue when connecting trough MWS from outside office to start OPM modules. Currently Integration team is solved the issue and the tool run again.
2 | Check OPM documentation is complete for all modules | 02/04/18 | César/Brayant | 02/04/18 | Finished | 02/04/18 | The documentation was not completed before closing handover with remote team. We will then finish it.
3 | Close Handover with remote team | 05/03/18 | César | 02/04/18 | Finished | 31/03/18 | We closed as: All documentation was delivered, however, detailed documentation only for Retriever/Dispatcher. We will be detailing Documentation for Parser/KPI BE. We downloaded all code and changed passwords of cloud environment and office server.
4 | Study OPM Documentation. | 02/04/18 | César/Brayant | 06/04/18 | In progress | --- | Due to different activities (Helping Alfreddy to solve issues in ECOSS#4/Searching for XML Files to share with analyzer/Finding issue with public IP, etc.) this activity will continue next week.
5 | Close OPM Doublecheck Documentation with remote team | 02/04/18 | César | 02/04/18 | Finished | 02/04/18 | Dispatcher was updated, however it doesn’t have significant update, we will be updating this documentation also.

## Slide 9: Actions W14
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS
6 | Finish test of OPM Performance in ECOSS#4 finding optimal configuration. | 05/03/18 | Alfreddy | 16/04/18 | In progress | --- | The monitoring of KPI values continues after solving issue with VPN. Trying new configuration in order to speed up the tool on ECOSS#4.
7 | Deliver manual with optimal configuration for OPM in ECOSS#4 VMWare. | 05/03/18 | Alfreddy | 20/04/18 | To do | --- | The manual will be started after the test has finished.
8 | Node List by Network | 12/03/18 | César/Brayant (BE) | 06/04/18 | Finished | --- | Finished and integrated with current running system. The queries for node list have enhanced timing response to few seconds.

## Slide 10: Pending Tasks and Required Support (1 / 2)
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS | REQUIRED SUPPORT
1 | Users Management with LDAP | 12/03/18 | César/Brayant | 1 month after confirmation | To do | --- | It implies to create a connection interface with existing LDAP users on client side. It is recommended to leave this task for future versions. | Needs to confirm with client if it is really needed or not as this task was not included in customer’s original requirements.
2 | SMS for Notifications | 12/03/18 | César/Brayant | 3 weeks after getting SMPP server | To do | --- |  | It needs an SMPP server for testing.
3 | Start Parser for Huawei | 23/03/18 | César/Brayant | 1 to 2 months after getting parameters catalog from customer | To do | --- |  | It requires that client provides the complete parameter’s catalog of counters, XML test files of their network and examples of processed data.

## Slide 11: Pending Tasks and Required Support (2 / 2)
# | ACTION | CREATED ON | RESPONSIBLE | TARGET DATE | STATUS | FINISHED ON | COMMENTS | REQUIRED SUPPORT
4 | Obtain instructions on how to prepare installation disk for OPM and define responsible | 05/03/18 | César/Brayant | 16/04/18 | To do | --- |  | 
5 | Create installation disk | 05/03/18 | César/Brayant | 20/04/18 | To do | --- |  | It requires the performance test of OPM in ECOSS#4 is finished as well as OPM manual with optimal configuration for ECOSS#4
6 | Check compatibility between browsers/Windows | 05/03/18 | Martín | 13/04/18 | Finished | 06/03/18 | Checked the previous cases where the issue on Windows was found and it’s solved now. Other issues found during the way are also solved. | 
7 | Changing behavior of parameters in order to filter them by type and speed up parameter loading in view (KPI Lab Section) | 02/04/18 | Brayant | Estimated three weeks after choosing method or receiving file from customer. | To do | --- | The tool is working fine using counters from standard KPI when creating new formula. In order to work with whole counters, new process is required. This is just enhancement to the original behavior. | We can solve by these options: 1.- Ask customer if they have parameter->nodeType mapping file for Ericsson. 2.- Change behavior of existing parser to include all counters. 3.- Create new parser exclusively for parameters (similar as topology parser).

## Slide 12: Suggestion on How to Deliver
After discussing with the team, we consider we can deliver the tool as this:
Instead of installation disk we can do PoC with customer after the tool test by Alfreddy is finished
(After 16th/April/2018).
We can deliver First Version for PoC and Ericsson files and let Pending Tasks 1 (LDAP), 2 (SMS Notifications), 3 (Huawei parser) and 7 ( Changing behavior of parameters) for next update.
We can create test users for PoC.

## Slide 13
Thank you