## Configuration
CONFIGURATION
Node | ecoss41 | ecoss42 | ecoss43 | ecoss44 | ecoss45 | ecoss46
RAM | 27 | 21 | 16 | 24 | 24 | 16
vCPU | 3 | 3 | 2 | 3 | 3 | 2
OS | CentOS7 (64 Bit) | CentOS7 (64 Bit) | CentOS7 (64 Bit) | CentOS7 (64 Bit) | CentOS7 (64 Bit) | CentOS7 (64 Bit)
HD-1 | 65 GB | 65 GB | 65 GB | 65 GB | 65 GB | 200 GB
HD-2 | 500GB | 500GB | 500GB | 500GB | 500GB | 300GB
Applications | ecoss41: cassandra-3.11.1; ecoss42: cassandra-3.11.1
| elasticsearch 6 | elasticsearch 6 | elasticsearch 6
RabbitMQ 3.6.10
|  |  |  | 3 x opm-retriever-1.1.5 | 3 x opm-retriever-1.1.5 | 2 x opm-retriever-1.1.5
|  |  |  | 1 x opm-dispatcher-0.0.1 | 1 x opm-dispatcher-0.0.1 | 1 x opm-dispatcher-0.0.1
|  |  |  | 1 x opm-parser-2.0.4 | 1 x opm-parser-2.0.4 | 1 x opm-parser-2.0.4
users-management-be-0.0.1
opm-kpibe-2.0.8
opm-be-1.1.3
opm-schedule-0.0.1
opm-topology-parser-1.0.0
Nginx
FE GUI - 1.0.20
Mounted OSS | ecoss44: OSS 4G MTY; ecoss45: OSS 3G MEX; ecoss46: OSS 3G CHI
|  |  |  | OSS 4G TIJ | OSS 3G TIJ | OSS 3G MTY
|  |  |  | OSS 4G QRO | OSS 3G QRO

## Test Result
TEST RESULT
AREA | Sub Area |  | Functionality | Comment
ACCOUNT | Create |  | OK
| Modify |  | OK
| Delete |  | OK
KPI LAB | ERICSSON
NOKIA
Huawei
DASHBOARD | ERICSSON | 12/24 hrs per node | OK | Need to refine
|  | KPI Level | OK | Need to re-check about threshold
|  | Number of Nodes | OK | Need to show label ERBS and SGSN in the graph
|  | Worst Nodes | OK | take about 20 seconds to show the data
|  | Best Nodes | OK | take about 20 seconds to show the data
|  | Last ROP KPI per node | OK | Need to refine the choice
CSV File
NOKIA
Huawei
REPORT | ERICSSON | Cell | OK | need many improvement
|  | Node | OK | need many improvement
|  | Region | OK | need many improvement
|  | Tech | OK | need many improvement
NOKIA
Huawei
LOADING STATUS | ERICSSON |  | OK | the process is less than 10 minutes
NOKIA
Huawei
NOTIFICATIONS | ERICSSON | Cell | NOK | No notification comes to my email as setup
|  | Node | NOK | No notification comes to my email as setup
|  | Region | NOK | No notification comes to my email as setup
|  | Tech | NOK | No notification comes to my email as setup
NOKIA
Huawei
SOFTALARMS | ERICSSON | Cell | NOK | Cannot setup schedule for soft alarm
|  | Node | NOK | Cannot setup schedule for soft alarm
|  | Region | NOK | Cannot setup schedule for soft alarm
|  | Tech | NOK | Cannot setup schedule for soft alarm
NOKIA
Huawei